## Slide 1: Dynamics 365 for Talent
4 week implementation

## Slide 2: Overview
Deliver Dynamics 365 for Talent for your organisation.
Cost £30,000 + Licenses
Delivery timeline – 4 weeks

## Slide 3: What’s included?
Attract
Transform talent acquisition
Onboard
Improved engagement and communication for new joiners
Core HR
Improved Career paths
Improve efficiencies of your HR team
Self Service
Full LinkedIn Integration for improved candidate management
Accelerate time to impact for new joiners
Reduce attrition
Intuitive portal for employees
Reduce workload of your HR team
Empower employees with learning paths
Better visibility for management

## Slide 4: Project Approach
Requirements validation, design and set-up – week 1
Implementation of Core HR – week 2
Implementation of Attract & Onboard – week 3
Implementation of Employee Self Service – week 4

## Slide 5
Dynamics 365 for Talent Project Timeline
Week 1
Week 2
Week 3
Week 4
Testing, training and feedback
Gather requirements
Phase 1
Phase 2
Phase 3
Phase 4
Set up environment
Design data migration
Org Structure set up
Compensation and benefits
Employee enrolment
Set up attract module and recruitment
Set up onboarding processes
Portal Set up
Self service processes
Approvals

## Slide 6: Dynamics 365 for Talent implementation Cost breakdown
Phase | Resources | Effort in Days | Cost
Phase 1 | Project Manager Lead D365 Consultant Functional D365 Consultant Engineer (environment set up) | 2 3 3 2 10 | £7,500
Phase 2 | Project Manager Lead D365 Consultant Functional D365 Consultant | 2 2 6 10 | £7,500
Phase 3 | Project Manager Lead D365 Consultant Functional D365 Consultant | 2 2 6 10 | £7,500
Phase 4 | Project Manager Lead D365 Consultant Functional D365 Consultant Developer | 2 2 4 2 10 | £7,500
Total |  | 40 | £30,000

## Slide 7: Licences
Full Licence - £30.16 per user per month
Team member - £6 per user per month
5 full licence minimum